## RetailIQ Agile Roadmap
RetailIQ - Agile Project Roadmap
| October |  | November |  | December |  | January |  | February |  | March
Tasks | Week 01 - 02 | Week 03- 04 | Week 01 - 02 | Week 03- 04 | Week 01 - 02 | Week 03- 04 | Week 01 - 02 | Week 03- 04 | Week 01 - 02 | Week 03- 04 | Week 01 - 02 | Week 03- 04
Project Setup & Architecture Design | Yes
Database Finalization & ER Diagram | Yes
Authentication & RBAC |  | Yes
Store & User Management Module |  | Yes | [5 empty] | Yes
Product & Category Management |  | Yes | Yes |  | Yes
Supplier & Purchase Orders Module |  |  | Yes | [5 empty] | Yes
Inventory Management |  |  |  | Yes
Customer Orders & Billing |  |  | Yes |  | Yes |  |  |  | Yes
Invoice Module Integration |  |  |  | Yes |  |  |  | Yes
Payment Integration | [5 empty] | Yes
Analytics Dashboard (Basic Reports) |  |  |  | Yes
Demand Forecasting Model | [9 empty] | Yes
Market Basket Analysis | [6 empty] | Yes
Dynamic Pricing Engine | [7 empty] | Yes
Stock-out & Overstock Prediction | [5 empty] | Yes | Yes |  |  | Yes |  | Yes
UI Enhancements & Performance Optimization |  | Yes |  | Yes |  |  | Yes |  | Yes |  | Yes
Testing (Unit + Integration)